## Sheet1
Agile Project Plan
Project Name | Product Release |  |  |  |  | Adapted from smartsheet
Project Manager | Alex B.
Project Deliverable
Scope Statement
Start Date | 2016-11-25
End Date | 2016-12-16
Overall Progress | 0%
Task Name | Responsible | Start | End | Days | Status
Sprint 1 |  | 2016-11-25 | 2016-12-01 | 6 | Completed
Create database |  | 2016-11-25 | 2016-11-26 | 1 | Completed
Create log in screen |  | 2016-11-26 | 2016-11-27 | 1 | Completed
Create patient form |  | 2016-11-28 | 2016-12-01 | 3 | Completed
Sprint 2 |  | 2016-12-02 | 2016-12-08 | 6 | Completed
Create appointment form |  | 2016-12-02 | 2016-12-04 | 2 | Completed
Create register arrival form |  | 2016-12-04 | 2016-12-05 | 1 | Completed
Create consultation form |  | 2016-12-06 | 2016-12-08 | 1 | Completed
Create report form |  | 2016-12-08 | 2016-12-09 | 1 | Completed
Sprint 3 |  | 2016-12-09 | 2016-12-16 | 7 | Completed
Create availability form |  | 2016-12-09 | 2016-12-10 | 1 | Completed
Create edit appointment form |  | 2016-12-11 | 2016-12-12 | 1 | Completed
Add buttons for all functionlaties to all forms |  | 2016-12-14 | 2016-12-16 | 2 | Completed
Sprint 4 |  | 2017-01-03 | 2017-01-08 | 5 | Completed
Get access rules working |  | 2017-01-03 | 2017-01-05 | 2 | Completed
Ensure all buttons simiulate functions (with message boxes, images, error messages, etc.) |  | 2017-01-05 | 2017-01-07 | 1 | Completed