## Sheet1
Agile Product Backlog
Task Name | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Sprint 1 | Yes | High | In Progress
Create database to store patients, consultations, access, doctors, etc | Yes | High | Complete
Create log in screen | Yes | High | Complete
Create patient form | No | High | Complete
Sprint 2 | Yes | High | In Progress
Create appointment form with an add appointment button | Yes | High | Complete
Create a register arrival form | Yes | High | Complete
Create a consultation form | Yes | High | Complete
Create a report form | Yes | High | Complete
Sprint 3 | Yes | High | Complete
Create availability form | Yes | High | Complete
Create edit appointment form | Yes | High | Complete
Create report form with buttons for each form | Yes | High | Complete
Add buttons for future fucntionalities to all forms | Yes | High | Complete
Sprint 4 | Yes | High | Not Started
Add database functionalities to all forms | Yes | High | Not Started
Create doctor appointment forms | Yes | High | Not Started
Create doctor cost forms | Yes | High | Not Started
Ensure there is access control on all forms | Yes | High | Not Stared

## Sheet2
This sheet is to enable the drop-down lists
Yes | High | Complete
No | Medium | In Progress
| Low | Not Started