## Sheet1
Sprint Backlog Template
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Sprint Review
Sprint 1
Create database |  |  | Completed | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Create log in screen |  |  | Completed | 2 | 0.5 | 2 | 0 | 0 | 0 | 0 | 0
Create patient form |  |  | Completed | 3 | 0 | 0 | 0 | 0 | 2 | 1 | 0
Sprint 2
Create appointment form |  |  | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Create report form |  |  | Completed | 1 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0
Create a consulation form |  |  | Completed | 1 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
Create register arrival from |  |  | Completed | 1 | 0 | 0 | 0.5 | 0 | 1 | 0 | 0
Sprint 3
Create availability form |  |  | Completed | 1 | 0.5 | 0 | 0 | 0 | 0 | 1 | 0
Create edit appoitnement form |  |  | Completed | 0.5 | 0 | 0.5 | 0.15 | 0 | 0 | 0 | 0
Include buttons all forms fo future functionlities |  |  | Completed | 0.45 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0
Sprint 4
Add database functionalities to all forms |  |  | Not Started | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create doctor appintment reports |  |  | Not Started | 1
Create doctor cost report |  |  | Not Started | 1
Ensure there is access control in place |  |  | Not Started | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  | 12.95 | 3.15 | 3 | 0.65 | 0.5 | 3.5 | 2 | 0
Create a Sprint Backlog in Smartsheet