## Sheet1
Sprint Backlog Template
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Sprint Review
Sprint 1
Create database |  |  | Completed | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Create log in screen |  |  | Completed | 2 | 0.5 | 2 | 0 | 0 | 0 | 0 | 0
Create patient form |  |  | Completed | 3 | 0 | 0 | 0 | 0 | 2 | 1 | 0
Sprint 2
Add functionality to the patient form |  |  | In Progress | 1 | 1 | 0 | 0 | 0 | 0 | 0.5 | 0
Create appointment form with add function |  |  | In Progress | 3 | 0.5 | 2 | 0 | 0 | 0 | 0 | 0
Create options to edit and cancel appointments |  |  | In Progress | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create a consulation form |  |  | Completed | 1.5 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Add register arrival function |  |  | In progress | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Allow doctor to update availability and consultation notes |  |  | In progress | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
Sprint 3
Create reports form |  |  | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create a report to show all appointments |  |  | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create a report to show appointments for specific doctors |  |  | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create report to show doctor cost |  |  | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  | 20.5 | 3 | 4 | 1 | 0 | 3 | 2.5 | 0
Create a Sprint Backlog in Smartsheet